## Slide 1
STATUS REPORT · WEEK 24
Project status
Scope, schedule, risk and the two decisions we need from this meeting.
YOUR TEAM · YOUR ORGANIZATION · MONTH 2026

## Slide 2
What we will cover
01
Headline
One line: on track, at risk, or off track.
02
Progress
What closed since the last report.
03
Schedule
Milestones, and any date that moved.
04
Risks
Ranked, with an owner and a next action.
05
Budget
Spend against plan, and the forecast.
06
Decisions
What we need agreed today.

## Slide 3
01
Progress
Delivered, in flight, and not started.

## Slide 4
HEADLINE
On track, with one date at risk
Lead with the verdict, not the narrative. State the overall status in one sentence, name the single thing most likely to change it, and say what you need in order to hold the date. Detail follows for the people who want it.
— Overall: on track for the September milestone.
— At risk: the integration date, pending a third-party fix.
— Mitigation: parallel path agreed, costs two weeks of effort.
— Needed today: a decision on scope for the second phase.

## Slide 5
WORKSTREAMS
Three streams, three states
01
Delivery
On plan. Six of eight components accepted.
02
Integration
At risk. Blocked on an external dependency.
03
Rollout
Not started. Begins once integration is accepted.

## Slide 6
THIS PERIOD
Progress and spend
74%
Scope complete
Accepted deliverables over total.
+3 d
Schedule variance
Against the baseline plan.
68%
Budget used
At 74% of scope — favourable.
2
Open risks
Both with an owner and a date.
Variance is measured against the baseline agreed in week 4, not against the last report.

## Slide 7
02
Risk
What could move the date, ranked by exposure.

## Slide 8
MILESTONES
Where the date stands
WK 4
Baseline
Scope and plan agreed and frozen.
WK 12
Build start
Environments handed over.
WK 24
Integration
External dependency outstanding.
WK 32
Acceptance
User testing, two-week window.
WK 36
Live
Phased cutover, rollback rehearsed.

## Slide 9
RISK REGISTER
Ranked risks
RISK
IMPACT
OWNER
NEXT ACTION
Third-party fix late
High
Integration lead
Escalate Friday
Test data incomplete
Medium
Delivery lead
Sourced by wk 26
Key person single point
Medium
Programme
Pairing from wk 25
Scope creep, phase 2
Low
Sponsor
Decision today
Replace the rows with your own figures. Keep one unit per column.

## Slide 10
EVIDENCE
One image, one idea
DROP AN IMAGE HERE
One chart the sponsor can read
Burn-up against the baseline, or milestones against dates. Whichever you pick, keep it the same chart every report — a sponsor should be able to compare this week to last week without re-reading the axis.
Caption the image: what it shows and where it came from.

## Slide 11
03
Decisions
The choices that need an owner in this room.

## Slide 12
“
Tell me the date is moving in week 24, not in week 34.
PROGRAMME SPONSOR

## Slide 13
Decisions needed
Two: the phase-two scope, and whether we fund the parallel integration path.
YOUR.NAME@EXAMPLE.COM · +00 000 0000 · EXAMPLE.COM